## WBS with Gantt Chart - BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | LANE LINE DETECTION
PROJECT MANAGER | SITI NABIHAH BINTI ABU BAKAR
COMPANY NAME | LANE HOLDING SDN BHD
DATE | 2020-11-12 | [5 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Initiation
1.1 | Project Charter | Nabihah | 2020-10-15 | 2020-10-18 | 3 | 100%
1.2 | Research | Maimunah | 2020-10-19 | 2020-10-23 | 4 | 90%
1.3 | Projections | Zulaikha | 2020-10-19 | 2020-10-25 | 6 | 90%
1.4 | Stakeholders | Khalid | 2020-10-21 | 2020-10-26 | 5 | 80%
1.5 | Guidelines | Khalid | 2020-10-21 | 2020-10-26 | 5 | 85%
1.6 | Project Initiation | Nabihah | 2020-10-22 | 2020-10-30 | 9 | 70%
2 | Project Planning
2.1 | Collect projects requirement | Nabihah | 2020-11-02 | 2020-11-05 | 3 | 70%
2.2 | Set up goal & scope | Maimunah | 2020-11-03 | 2020-11-06 | 3 | 100%
2.3 | Create WBS | Khalid | 2020-11-09 | 2020-11-12 | 3 | 90%
2.4 | Verify & control scope | Zulaikha | 2020-11-10 | 2020-11-13 | 3 | 80%
3 | Project Execution
3.1 | Status & tracking | Maimunah |  |  |  | 0%
3.2 | KPIs | Nabihah |  |  |  | 0%
3.3 | Monitoring | Nabihah |  |  |  | 0%
3.4 | Forecast | Zulaikha |  |  |  | 0%
3.5 | Project Updates | Khalid |  |  |  | 0%
3.6 | Chart Updates | khalid |  |  |  | 0%
4 | Project Performance/Monitoring
4.1 | Projects objectives | Zulaikha |  |  |  | 0%
4.2 | Quality Deliverables | Maimunah |  |  |  | 0%
4.3 | Effort & Cost Tracking | Khalid |  |  |  | 0%
4.4 | Project Testing | Nabihah |  |  |  | 0%
GROUP MEMBERS 1)Siti Maimunah binti Abdul Rahman (B031810418) 2)Siti Nabihah binti Abu Bakar (B031810408) 3)Siti Zulaikha binti Azman (B031820029) 4)Khalid Tewfik Mohamed (B031810452)