## Communications Guide
Communications Guide
Introduction | The Communication Plan is a draft of the communication approach and activities related to the project among the stakeholders, both internal and external.
Timing | The Communication Plan should be developed during these three phases of PMLC (Project Management Life Cycle): Planning, Analysis and Design
Communication Plan | The Communications Plan describes project key messages, branding, visual appeals, stakeholder needs and communication events.
Messaging | Key messages are the important statements about a project the team wishes to share with stakeholders. The method of the delivering message might differs between stakeholders depending on the information type and stakeholders' preferences. The communication should focused on key facts and motive. Depending on the project, it may be important to both repeat some key messages over the life of the project, and introduce new messages as the project progresses.
Executive Staff | Recommend use External Relations and have Executive Sponsor Approval
Factory | Recommend use External Relations and have approvals from Executive Sponsor, Manufacture Manager and IT Department's Office
Staff | Recommend use External Relations and have approval from Executive Sponsor
Tester | Recommend use External Relations and have approvals from Executive Sponsor and Tester Expert
External Stakeholders | Recommend use External Relations and have Executive Sponsor Approval
Messaging Medium | Some of the communication two parties to meet up, phone calls, instant messages and might also represented through visualization tools: PPT, Website, Notice
Infomail Protocol and Guidelines | Provides an overview of protocols and guidelines as related to distribution of update, information and urgent notices to staffs, testers, managers and developers. Type of communication needed to be used and general information are described in the guide.
Branding and Visual Identity | All branding and visual identity must be referred to the GW standards. Contact External Relations for guidelines.
Budget | All communications are bounded by the budget allocated for communication items and needs. Printed materials and paid-software for communication will be considered as communication needs which fall under communication budget.

## Communications Sample Entri
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Audience | Reviewer | Company/Staff
1 | Reminder emails to team's project | email | on-going | weekly | Update progress about the project with the team members | All team project | Project manager, rocurement manager, Operation manager | Staff
2 | Memo for meeting online | email,website | on-going | weekly | Update the information about the up coming meeting | Project Schedule, Development team, Procurement manager, Operation manager, Risk manager | Project manager | Staff

## LLD project Communications
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Audience | Reviewer | Company / Staff | Owner
1 | Project Team Communication | Meeting | Ongoing | Weekly | Weekly status meeting to discuss schedule, communications, actions, risks & issues | Project Team | Nurul Asyikin | Staff | Nabihah
2a | Executive Sponsor Communication | PPT | Ongoing | Weekly | Weekly status report to executive sponsors for overview of the project progress | Executive Sponsors - Alibaba Holdings, Datin Nur Farahin & Dato Aaron Aziz | Yasin Syukor,Lee Yong Wei | Staff | Maimunah
2b | Executive Sponsor Communication | Meeting | Ongoing | Monthly | Monthly executive overview of the project progress | Executive Sponsors - Alibaba Holdings, Datin Nur Farahin & Dato Aaron Aziz | Amir Muslim, Michelle Wiles | Staff | Maimunah
3 | Communication with car manufacturer | Meeting | Ongoing | Monthly | Monthly meeting on implementin this system into new cars | Automobil engineers | Saiful Asyraf
4 | Merit Liaison & FDs roles & responsibility | Email | 2020-09-14 | One-time | Create list of responsibilities for merit liaisons (e.g. communicate appropriate information to supevisors, dept heads, AVP's etc.) | Merit Liaisons & all FDs | Pavithra | Staff | Nabihah
5 | Communication to departments regarding grade minimums. | Email | 2020-09-15 | One-time | Will include instructions on ways to notify employees. | Merit liaisons | Pavithra | Staff | Zulaikha
6 | FORMAL: Testing result notification and documentation | Email | 2020-09-15 | One-time | include all the details on test result, test case of the projects. | Executive Sponsors - Alibaba Holdings, Datin Nur Farahin & Dato Aaron Aziz | Nurul Asyikin | Staff | Khalid
7 | Company's project guidance | Letter | 2020-09-15 | One-time | Describes the projects test case, holdback, functionality. | Staff | Rashid Rahman | Staff | Khalid
8 | Creation and distribution of letters to employees impacted by grade minimum change | N/A | 2020-09-25 | One-time |  |  | Rashid Rahman | Staff | Maimunah
9 | FAQ's | Webpage | 2020-09-29 | One-time | Can't finish web page until we have clarification from on dates. | Project Team | Rashid Rahman, Nurul Asyikin | Staff | Zulaikha
10 | Create additional webpage content for advertisement | Webpage | 2020-09-30 | One-time | Can't finish web page until we have clarification from on dates. | Project Team | Rashid Rahman, Nurul Asyikin | Staff | Khalid
11 | Final testing result | Email | 2020-12-10 | One-time | All the details on the testing of the projects will be updated to sponsors and future clients. | Executive Sponsors - Alibaba Holdings, Datin Nur Farahin & Dato Aaron Aziz | Amir Muslim, Michelle Wiles | Staff | Nabihah
12 | Creation of lane line worksheet guidance (first tab of merit workbooks) | XLS |  | One-time |  |  |  | Staff
13 | Reminder emails to manufacturer and programmer to return final spreadsheets on or before 11/15 | XLS | 11/28, 11/3, 11/9, 11/15, | Every 4 days until s/s returned | Mitigation for risk of late spreadsheets | Project Team, manufacturer | None | Staff | Maimunah